## Sheet1
GOAL | WEEK | DATES | GENERAL TASKS
Project Definition and Proposal | 1 | 3 May - 9 May | - Select/Define Project - Create Project Management Tools - Write Project Proposal - Start Project Background/Data Review
Data and Systems Understanding | 2 | 10 May - 17 May | - Continue Project Background/Data Review - Select Project Data and Complete EDA - Understand Data Systems Architecture - Learn InfluxDB - Simulate Streaming in InfluxDB - Begin Research/Modelling for Anomaly Detection
Anomaly Detection Model | 3 | 18 May - 24 May | - Continue Anomaly Detection Research - Complete Data Cleaning/Feature Steps in Pipeline - Build Anomaly Detection Model - Start Learning/Understanding Azure
Implement Streaming Pipeline | 4 | 25 May - 31 May | - Complete Anomaly Detection Model in Pipeline - Model Tuning and Evaluate Performance - Intermediate Presentation for Following Week
Value Week | 5 | 1 June - 7 June | Dependent on Time and in Discussion with UDL Select One or Two of: - Complete Unfinished Week 2-4 Tasks - Twinning System in Azure - Scale Pipeline to Another System - Improve Anomaly Detection Model - Start Dashboard to Provide a Higher Quality Dashboard Product
Dashboard | 6 | 8 June - 13 June | - Create and Complete Dashboard - Final Pipeline Wrap-up
Reporting | 7 | 14 June - 22 June | - Code/Project Clean-up - Draft and Final Report - Client and MDS Presentations

## Sheet2
Appendix A - Project Schedule
|  | May 3, 2021 |  |  |  |  | May 10, 2021 |  |  |  |  | May 17, 2021 |  |  |  |  | May 24, 2021 |  |  |  |  | May 31, 2021 |  |  |  |  | June 7, 2021 |  |  |  |  | June 14, 2021
|  | Project Definition and Proposal |  |  |  |  | Data and Systems Understanding |  |  |  |  | Anomaly Detection Model |  |  |  |  | Implement Streaming Pipeline |  |  |  |  | Value Week |  |  |  |  | Dashboard |  |  |  |  | Reporting
TASKS | WEEK | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22
|  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T
Project Definition and Proposal
Select/Define Project | 1
Create Project Management Tools | 1
Write Project Proposal | 1
Project Background/Data Review | 1
Data and Systems Understanding
Select Project Data and Complete EDA | 2
Understand Data Systems | 2
Learn InfluxDB | 2
Simulate Streaming in InfluxDB | 2
Anomaly Detection Research | 2
Anomaly Detection Model
Meet with Domain Experts | 3
Data Cleaning/Feature Steps in Pipeline | 3
Build Anomaly Detection Model | 3
Review Azure | 3
Implement Streaming Pipeline
Streaming Anomaly Detection Pipeline | 4
Model Tuning and Evaluate Peformance | 4
Status Presentation | 4
Value Week
One or More of the Items in Notes | 5
Dashboard
Create and Complete Dashboard | 6
Reporting
Final Project Report | 7
Final Presentation | 7
Project Wrap-up | 7
Note: Value week will consist of one or more of the following based on priorities
1) Finish Outstanding Week 2-4 Tasks
2) Implement in Azure
3) Scale to Additional Data Systems
4) Explore/Implement TinyML-Edge AI
5) Improve Anomaly Detection Model
6) Start Dashboard