## Week 1
Ryan Koenig
2021-05-03
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 1
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-03
Internal kick-off meeting | Internal Meetings | 0.5
Client kick-off meeting | Client Meetings | 1
Internal post-client meeting | Internal Meetings | 0.5
Discuss and write team-contract.md and initial planning | Internal Meetings | 1
Start Proposal outline | Project Documents | 1
4
2021-05-04
Background Research | Project Documents | 1.5
MDS capstone kick-off meeting | UBC Meetings | 2
Proposal work | Project Documents | 1
Review links provided by client | Background Review | 1
Internal meeting to discuss proposal and next client meeting | Internal Meetings | 0.5
Proposal work | Project Documents | 2
8
2021-05-05
Proposal work | Project Documents | 3
Client Meeting | Internal Meetings | 1
Internal post-client meeting | Internal Meetings | 0.25
Proposal work | Project Documents | 3
7.25
2021-05-06
Proposal Editing | Project Documents | 0.5
Internal meeting | Internal Meetings | 0.5
Proposal Schematic Design | Project Documents | 1
Proposal Editing | Project Documents | 1.5
Client Meeting Sprint Meeting | Internal Meetings | 0.5
Post-Client Meeting | Internal Meetins | 0.25
Proposal Editing | Project Documents | 2
6.25
2021-05-07
Internal Meeting | Project Documents | 0.5
0.5
2021-05-08
Proposal Figure Updates | Project Documents | 0.5
0.5
2021-05-09
Internal Meeting | Internal Meeting | 0.5
EDA Research and Design | Project Documents | 3
3.5
TOTAL |  | 30
ADDITIONAL COMMENTS

## Week 2
Ryan Koenig
2021-05-10
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 2
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-10
EDA Investigation | Project Documents | 2
Internal morning meeting | Internal Meetings | 0.5
EDA Investigation | Project Documents | 3
Client Meeting | Internal Meetings | 1
Post-Client Meeting | Internal Meetings | 0.5
Influxdb and Telegraf install | Software Setup | 1
8
2021-05-11
Influxdb and Telegraf setup | Software Setup | 1
Proposal Presentation Preperation | Project Documents | 1
Internal morning meeting | Internal Meetings | 1
Influxdb Investigation | Software Setup | 1.5
Proposal Presentation Preperation | Internal Meetings | 0.5
Telegraf Setup | Software Setup | 2
7
2021-05-12
Telegraf JSON parsing | Software Setup | 2
Internal morning meeting | Internal Meetings | 1
Telegraf JSON parsing | Software Setup | 7
10
2021-05-13
EDA Prep | Project Documents | 2
Internal morning meeting | Internal Meetings | 0.5
Client Meeting | Internal Meetings | 0.25
Telegraf Setup | Software Setup | 3
Telegraf Setup | Software Setup | 2.5
8.25
2021-05-14
Telegraf Finalizing | Software Setup | 2
Internal morning meeting | Internal Meetings | 0.25
EDA Prep | Project Documents | 3
5.25
2021-05-15
EDA Prep | Project Documents | 3
3
2021-05-16
EDA Prep | Project Documents | 5
5
TOTAL |  | 46.5
ADDITIONAL COMMENTS

## Week 3
Ryan Koenig
2021-05-17
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 3
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-17
EDA Work | Project Documents | 1
Internal morning meeting | Internal Meetings | 0.5
EDA Work | Project Documents | 1
Client Meeting | Internal Meetings | 1
Post-Client Meeting | Internal Meetings | 0.5
EDA Work | Project Documents | 2
Telegraf Debugging | Software Setup | 3
9
2021-05-18
EDA Work | Project Documents | 1
Presentation Prep | Project Documents | 1
EWS Meeting | External Meeting | 1
Internal morning meeting | Internal Meetings | 0.5
Week 3 Update Presentation | Internal Meetings | 0.75
Telegraf Debugging | Software Setup | 1
Anomaly Research | Research | 3
8.25
2021-05-19
Anomaly Research | Research | 2
Internal morning meeting | Internal Meetings | 0.5
Anomaly Research | Research | 5
7.5
2021-05-20
Anomaly Research | Research | 1
Internal morning meeting | Internal Meetings | 1.5
Telegraf Debuggin | Software Setup | 2
LSTM Schematic | Project Documents | 2.5
Slide Show Prep | Project Documents | 1
8
2021-05-21
Presentation Work | Project Documents | 1.5
Interal morning meeting | Internal Meetings | 0.5
Domain Expert Meeting | Internal Meetings | 1
Meeting with Scott | Internal Meetings | 0.5
Internal Meeting | Internal Meetings | 0.5
Prep Work | Project Documents | 2
6
2021-05-22
Downloading Data | Database Building | 3
Script for Cleaning Data | Database Building | 1.5
Downloading Data | Database Building | 0.5
Editing Script for Data | Database Building | 0.5
5.5
2021-05-23
0
TOTAL |  | 44.25
ADDITIONAL COMMENTS