## Slide 1: Realtime Anomaly Detection for Building Sensors Urban Data Lab Capstone Project Week 7 Status
Data 599 Mitch Harris, Ryan Koenig, Nathan Smith June 15, 2021

## Slide 2: Outline
Previous Week Summary (June 7 – 13)
Next/Final Week Planning (June 14 – 22)
Timeline Reflection

## Slide 3: Previous Week Summary
Week 6 Goals: Dashboard
Final Model Testing
Work on Report
Dashboard
Wrap-up Model Implementation

## Slide 4: Week 6 Tasks Previous Week (June 7 - 13)
Final Model Testing
Selected threshold rule and default window length
Downloaded an additional 5 sensors (had to do this manually)
Summarized results
Evaluating 5 additional sensors Monday but now complete

## Slide 5: Week 6 Tasks Previous Week (June 7 - 13)

## Slide 6: Week 6 Tasks Previous Week (June 7 - 13)

## Slide 7: Week 6 Tasks Previous Week (June 7 - 13)
Continued Reporting
Mainly complete, just needs additional results and several figures
Targeting final draft report completion for Wednesday
Already started final presentation
On track (and ahead of schedule)

## Slide 8: Week 6 Tasks Previous Week (June 7 - 13)
Dashboard and Notification System
Simple dashboard built directly into InfluxDB
Simple notification system – if an anomaly is predicted for a sensor a notification is sent to a Slack channel
Still finishing dashboard and notification system – wrapping up today

## Slide 9: Week 6 Tasks Previous Week (June 7 - 13)

## Slide 10: Week 6 Tasks Previous Week (June 7 - 13)
Model Implementation
Implementation in test environment with notebook walk-through
Still needs additional work
As real-time data streaming to InfluxDB is not available this will be the main implementation
Additional work required on this during the week

## Slide 11: Challenges Previous Week (June 7 - 13)
Wrap-up
Needed to focus on wrapping up scope
Test environment walkthrough added some scope
Dashboard
Dashboard didn’t go as fast as hoped – while the Dashboard implementation in InfluxDB is easy, Boolean data is not handled well

## Slide 12: Client Meetings Previous Week (June 7 - 13)
Thursday Sprint Planning
Plan for next week tasks, discuss final project wrap-up
Provide draft report to UDL Wednesday EOD
Present to UDL the following Wednesday

## Slide 13: Time Summary Previous Week (June 7 - 13)

## Slide 14: Next/Final Week Planning
Week 7 Goals: Reporting
Complete Report
Complete Presentation
Complete Walkthrough/Code/Repo Wrap-up Code

## Slide 15: Individual Tasks Next Week (June 14 - 22)
Mitch: Complete Dashboard and Package Wrap-up
Ryan: Results Section of Report
Nate: Report, Presentation, Walkthrough, and Repo Wrap-up
We have a detailed daily task list to ensure we’re on track

## Slide 16: Challenges Next Week (June 14 - 22)
Stick to Wrap-up and schedule

## Slide 17: Timeline Reflection

## Slide 18: Schedule Timeline Reflection
Week 6:
Dashboard (complete today)
Complete final model tests (complete Monday)
Continued reporting (ahead of schedule)
Test environment (not completed, ongoing)
Week 7:
Finish report and presentation
Finish dashboard and walkthrough
Wrap-up code/repo
Week | Goal
1 | Project Definitional and Proposal
2 | Data and System Understanding
3 | Anomaly Detection Model
4 | Implement Streaming Pipeline
5 | Value Week
6 | Dashboard
7 | Reporting

## Slide 19: Impacts to Schedule Timeline Reflection
It’s going to be busy but we believe doable

## Slide 20: Thank You
Mitch Harris
Ryan Koenig
Nathan Smith