## Week 1
Mitch Harris
2021-05-03
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 1
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-03
Internal kick-off meeting | Internal Meetings | 0.5
Client kick-off meeting | Client Meetings | 1
Internal post-client meeting | Internal Meetings | 0.5
Discuss and write team-contract.md and initial planning | Internal Meetings | 1
3
2021-05-04
Background Research | Background Review | 1
MDS capstone kick-off meeting | UBC Meetings | 2
Create gantt chart | Project Documents | 6
Review links provided by client | Background Review | 1
Internal meeting to discuss proposal and next client meeting | Internal Meetings | 0.5
10.5
2021-05-05
Literature review | Background Review | 6
Client Meeting | Client Meetings | 1
Internal post-client meeting | Internal Meetings | 0.25
7.25
2021-05-06
Literature review | Background Review | 3
Internal meeting | Internal Meetings | 0.5
Client Meeting Sprint Meeting | Client Meetings | 0.5
Post-Client Meeting | Internal Meetings | 0.25
4.25
2021-05-07
Internal Meeting | Project Documents | 0.5
Literature review | Background Review | 1.5
2
2021-05-08
0
2021-05-09
Reseached existant python modules for online anoamly detection | Backgorund Review | 3
3
TOTAL |  | 30
ADDITIONAL COMMENTS

## Week 2
Mitch Harris
2021-05-10
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 2
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-10
Anomaly Decection Package Research | Background Research | 6
Stand-up | Internal Meetings | 0.25
Docker with influx set up | Parsing Files | 1.5
Meeting with UDL to discuss InfluxDB/Telegraf | Client Meeting | 1.25
Post-meeting internal discussion | Internal Meetings | 0.5
9.5
2021-05-11
Anomaly deteciton package research | Background Research | 1
Stand up and presentation run through | Internal Meetings | 0.75
Data 599 presentation | Internal Meetings | 0.5
Model & package research | Background Research | 5
7.25
2021-05-12
Stand up | Interal Meetings | 0.5
Model Research | Background Research | 6
6.5
2021-05-13
Stand up | Internal Meetings | 0.5
Meeting to figure out Docker | Internal Meetings | 0.5
Sprint Planning | Client Meeting | 1
Figure out Docker | Infrastructure set up | 6
8
2021-05-14
Stand up | Internal Meeting | 0.5
Test different Modeling Frameworks | Coding | 3
Test different Algorithms for different types of anomalies | Coding | 3
6.5
2021-05-15
0
2021-05-16
0
TOTAL |  | 37.75
ADDITIONAL COMMENTS

## Week 3
Mitch Harris
2021-05-17
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 3
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-17
Anomaly Decection Package Research | Background Research | 3
Stand-up | Internal Meetings | 0.5
Work on power point for presentation | Reporting | 2
Meeting with UDL | Client Meeting | 1
6.5
2021-05-18
Anomaly deteciton package research | Background Research | 1
Stand up and presentation run through | Internal Meetings | 0.75
Data 599 presentation | Internal Meetings | 0.667
Model & package research | Background Research | 4
6.417
2021-05-19
Stand up | Interal Meetings | 0.5
Model Research | Background Research | 5.5
6
2021-05-20
Stand up | Internal Meetings | 1
LSTM research and demo | Code | 6
Sprint Planning | Client Meeting | 1
8
2021-05-21
Stand up | Internal Meeting | 0.5
Meeting with UDL and EWS | Client Meeting | 1
Meeting with Captstone Advisor | Advisor Meeting | 0.667
Advisor Follow up meeting | Internal Meeting | 0.333
Work on labeling data | Coding | 1
Model Pipeline Architecture | Coding | 3
6.5
2021-05-22
Model Pipeline Architecture | Coding | 2
2
2021-05-23
Build Flask App for serving models | Coding | 5
5
TOTAL |  | 40.417
ADDITIONAL COMMENTS

## Week 4
Mitch Harris
2021-05-24
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 4
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-24
LSTM research and testing | Background Research | 4
Stand-up | Internal Meetings | 0.75
4.75
2021-05-25
Stand up | Internal Meetings | 0.67
Data 599 presentation | Internal Meetings | 0.67
Presentation follow up | Internal Meetings | 0.33
Prediction Pipeline creation | Coding | 5
6.67
2021-05-26
Stand up | Interal Meetings | 0.33
Implementing predictions with flask | Coding | 6
Pipeline discussion call | Interal Meetings | 0.67
7
2021-05-27
Stand up | Internal Meetings | 0.5
Pipeline support for groupmate | Internal Meetings | 2
Sprint Planning | Client Meeting | 0.5
Model Evaluation Notebook | Coding | 2
Implementing predictions on loop without flask | Coding | 2
Post sprint planning meeting | Internal Meetings | 0.5
`
7.5
2021-05-28
Stand up | Internal Meeting | 0.5
Create model evaluation notebook template | Coding | 8
Notebook template demo | Internal Meeting | 0.75
9.25
2021-05-29
Update model evaluation notebook template | Coding | 2
Research LSTMs | Background research | 2
Group call | Internal Meeting | 0.5
4.5
2021-05-30
Meeting with Nate to be updated on LSTM modifications | Internal Meeting | 0.75
0.75
TOTAL |  | 40.42
ADDITIONAL COMMENTS

## Week 5
Mitch Harris
2021-05-31
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 5
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-31
Understand Influx | Background Research | 3
Stand-up | Internal Meetings | 0.5
UDL meeting | Client Meeting | 0.5
Presentation run though | Internal Meetings | 1
Understand Pipeline code | Coding | 1
6
2021-06-01
Stand up / Presentation practice | Internal Meetings | 0.5
Data 599 presentation | Internal Meetings | 0.33
Learn Influx | Coding | 5
5.83
2021-06-02
Stand up | Interal Meetings | 0.67
Write test env pipeline | Coding | 6
Learn/Understand Influx | Background research | 2
8.67
2021-06-03
Stand up | Internal Meetings | 0.25
Create Test env | Coding | 6
Sprint Planning | Client Meeting | 1
`
7.25
2021-06-04
Stand up | Internal Meeting | 0.33
Test env set up with influx | Coding | 6
Learn/Understand Influx | Background Research | 2
8.33
2021-06-05
Test Env set up and PR | Coding | 5
5
2021-06-06
0
TOTAL |  | 41.08
ADDITIONAL COMMENTS

## Week 6
Mitch Harris
2021-06-07
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 6
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-06-07
Create Test Environment | Coding | 6
Stand-up | Internal Meetings | 1
7
2021-06-08
Stand up / Presentation practice | Internal Meetings | 0.67
Data 599 presentation | Internal Meetings | 0.33
Create Test Enviornment | Coding | 5
6
2021-06-09
Test Env notebook Call | Internal Meeting | 0.5
Stand up | Internal Meeting | 0.5
Second Call about Test Env | Internal Meeting | 0.67
Create Test Environment | Coding | 6
7.67
2021-06-10
Stand up | Internal Meetings | 0.25
Create InfluxDB Dashboard | Coding | 6
Sprint Planning | Client Meeting | 0.67
`
6.92
2021-06-11
Stand up | Internal Meeting | 0.25
Connect Dashboard with test env | Coding | 7
7.25
2021-06-12
0
2021-06-13
Create InfluxDB Dashboard Notifications | Coding | 5
5
TOTAL |  | 39.84
ADDITIONAL COMMENTS