## Week 1
Nathan Smith
2021-05-03
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 1
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-03
Start setting up project templates | Project Management | 1
Internal kick-off meeting | Internal Meetings | 0.5
Client kick-off meeting | Client Meetings | 1
Internal post-client meeting | Internal Meetings | 0.5
Discuss and write team-contract.md and initial planning | Internal Meetings | 1
Email client selection of project | Client Communication | 0.75
Start proposal powerpoint | Project Documents | 1
Clubhouse setup, branch protection, merge template PR, Slack workspace | Project Management | 1.5
Previous project review, Gantt chart options | Project Management | 3
10.25
2021-05-04
Templates for meeting minutes, stand-ups, and sprints | Project Management | 1.5
MDS capstone kick-off meeting | UBC Meetings | 2
Work on proposal powerpoint | Project Documents | 0.5
Review links provided by client | Background Review | 1
Setup meeting agenda and sprint plan for meeting next day | Project Management | 0.75
Internal meeting to discuss proposal and next client meeting | Internal Meetings | 0.5
Correspondence with client and setup docs in OneDrive with client | Client Communication | 0.5
Add WorkLog template, transfer logs, PR template branch | Project Management | 0.5
Discuss Gantt chart and tasks | Internal Meetings | 0.5
7.75
2021-05-05
Update Gantt chart and upload to OneDrive for client | Project Documents | 1
Stand-up | Internal Meetings | 0.25
Work on proposal/review progress to date on it | Project Documents | 1
Meeting with client to discuss project | Client Meetings | 0.75
Internal post client meeting | Internal Meetings | 0.5
Update meeting minutes | Client Communication | 0.5
Update Gantt chart | Project Documents | 0.25
Work on proposal statement of work section | Project Documents | 2.25
6.5
2021-05-06
Work on proposal | Project Documents | 2
Stand-up | Internal Meetings | 0.25
Work on proposal | Project Documents | 1.25
Scrum meeting with client | Client Meetings | 0.75
Kanban board organization and scrum meeting document clean-up | Project Management | 0.75
Finish draft proposal | Project Documents | 1.75
6.75
2021-05-07
Update proposal with client comments | Project Documents | 1.5
Stand-up | Internal Meetings | 0.25
Proposal Presentation | Project Documents | 2.5
High-level review of anomaly detection algorithms | Background Review | 1.5
5.75
2021-05-08
Finalize proposal and presentation | Project Documents | 1
Update GitHub READMEs | Project Management | 0.5
1.5
2021-05-09
0
TOTAL |  | 38.5
ADDITIONAL COMMENTS

## Week 2
Nathan Smith
2021-05-10
Master of Data Science Capstone Project - 2021 |  |  | Week #
University of British Columbia - Okanagan |  |  | 2
Kelowna, BC
CLIENT
Urban Data Labs
DESCRIPTION | Activity Type | HRs
2021-05-10
Review InfluxDB docs, run UDL SkySpark example | Understand InfluxDB | 2
Stand-up | Internal Meetings | 0.25
Review InfluxDB docs to understand how streaming architecture would work | Understand InfluxDB | 2.25
Meeting with UDL to discuss InfluxDB/Telegraf | Client Meeting | 1.25
Post-meeting internal discussion | Internal Meetings | 0.5
Write-up meeting minutes | Project Documents | 0.25
Working on getting InfluxDB and Telegraf running locally | Parsing Files | 4.5
11
2021-05-11
Working on getting InfluxDB and Telegraf running locally | Parsing Files | 1.25
Logs and GitHub cleanup | Project Management | 0.25
Research how streaming anomaly detection would wrok with InfluxDB | InfluxDB Streaming | 0.25
Stand-up and presentation run-through | Internal Meetings | 0.75
2.5
2021-05-12
0
2021-05-13
0
2021-05-14
0
2021-05-15
0
2021-05-16
0
TOTAL |  | 13.5
ADDITIONAL COMMENTS