## Week 1
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 12 |  |  | 12 | 12.18%
Meetings (internal, UBC, client) | 12 | 9 | 9.5 | 30.5 | 30.96%
Background Review | 2.5 | 2.5 | 14.5 | 19.5 | 19.8%
Proposal (presentation and report) | 12 | 15.5 | 6 | 33.5 | 34.01%
EDA |  | 3 |  | 3 | 3.046%
Total | 38.5 | 30 | 30 | 98.5 | 100%
Notes: | Meetings appear under-reported by Mitch/Ryan

## Week 2
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 8 |  |  | 8 | 5.787%
Meetings (internal, UBC, client) | 6 | 5.5 | 5.25 | 16.75 | 12.12%
InfluxDB/Telegraf/Docker: Understand/Streaming Framework/Simulation | 29.5 | 5.5 | 7.5 | 42.5 | 30.74%
Parsing with Telegraf to support UDL | 10.5 | 16.5 |  | 27 | 19.53%
EDA (limited) |  | 18 |  | 18 | 13.02%
Proposal (presentation and report) |  | 1 |  | 1 | 0.7233%
Anomaly Detection Research / Testing Packages |  |  | 25 | 25 | 18.08%
Total | 54 | 46.5 | 37.75 | 138.25 | 100%
Notes: | Items not considered in project proposal

## Week 3
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 8 | 7 | 2 | 17 | 11.02%
Meetings (internal, UBC, client) | 8 | 8.25 | 7.5 | 23.75 | 15.4%
InfluxDB/Telegraf/Docker: Understand/Streaming Framework/Simulation | 16 |  |  | 16 | 10.37%
Parsing with Telegraf to support UDL | 2.75 | 7 |  | 9.75 | 6.321%
Dashboard Research | 4 |  |  | 4 | 2.593%
EDA | 0.75 | 3 |  | 3.75 | 2.431%
Anomaly Detection Research / Model Selection | 4 | 11.5 | 31.25 | 46.75 | 30.31%
Misc (Github Token Issue) | 2 |  |  | 2 | 1.297%
Anomaly Labelling (build app and label anomalies) | 19 | 4 |  | 23 | 14.91%
Manual Data Downloads | 0.25 | 8 |  | 8.25 | 5.348%
Total | 64.75 | 48.75 | 40.75 | 154.25 | 100%
Notes: | Items not considered in project proposal

## Week 4
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 5 | 0.5 | 0 | 5.5 | 3.673%
Meetings (internal, UBC, client) | 5.5 | 5.5 | 6.25 | 17.25 | 11.52%
Status Presentation | 4.25 | 0 | 0 | 4.25 | 2.838%
Report | 2 | 0.5 | 0 | 2.5 | 1.669%
Build Model Pipeline (Code/Research) | 24.5 | 31 | 34.25 | 89.75 | 59.93%
Evaluate Preliminary Results | 8.75 | 15 | 0 | 23.75 | 15.86%
Anomaly Labelling / Data Access | 6.75 | 0 | 0 | 6.75 | 4.508%
Total | 56.75 | 52.5 | 40.5 | 149.75 | 100%
Notes: | Items not considered in project proposal

## Week 5
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 4.25 | 0.75 | 0 | 5 | 3.953%
Meetings (internal, UBC, client) | 6 | 5 | 3.25 | 14.25 | 11.26%
Status Presentation | 6.25 | 8 | 3 | 17.25 | 13.64%
Report | 26 | 0 | 0 | 26 | 20.55%
Implement Model | 0.5 | 0 | 34 | 34.5 | 27.27%
Model Tuning/Results | 1.5 | 28 | 0 | 29.5 | 23.32%
Total | 44.5 | 41.75 | 40.25 | 126.5 | 100%
Notes:

## Week 6
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 4.75 | 0.5 | 0 | 5.25 | 4.11%
Meetings (internal, UBC, client) | 3.25 | 3.25 | 3.25 | 9.75 | 7.632%
Report / Final Presentation | 24 | 10 | 0 | 34 | 26.61%
Results | 2.25 | 26.5 | 0 | 28.75 | 22.5%
Project Clean-up (repo, etc) | 2.5 | 0 | 0 | 2.5 | 1.957%
Test Environment Demo | 3 | 0 | 18.75 | 21.75 | 17.03%
Dashboard | 5.75 | 0 | 18 | 23.75 | 18.59%
Data Downloads/Processing | 2 | 0 | 0 | 2 | 1.566%
Total | 47.5 | 40.25 | 40 | 127.75 | 100%
Notes: | Scope not considered in proposal

## Week 7
Task | Nate | Ryan | Mitch | Total | Percent Total
Project Management (incl. documents/communication) | 2.75 | 0 |  | 2.75 | 2.461%
Meetings (internal, UBC, client) | 4.25 | 5.25 |  | 9.5 | 8.501%
Report / Final Presentation | 13.75 | 21 |  | 34.75 | 31.1%
Project Clean-up (final code, repo wrap-up) | 21.75 | 19.5 |  | 41.25 | 36.91%
Model Stability Check | 4.5 | 14.5 |  | 19 | 17%
Dashboard | 4.5 | 0 |  | 4.5 | 4.027%
Total | 51.5 | 60.25 | 0 | 111.75 | 100%
Notes: | Does not include Mon-Wed June 21-23, 2021